## 1. Cover
ACELI LAT — BUDGET, TIMELINE & COSTING
Revised Competitive Bid ¦ All amounts in USD ¦ Issued 2026-06-19
Document Title | Aceli LAT — Master Budget, Development Timeline & Costing Workbook (Rebid v2.0)
Project Name | Aceli LAT — Lender Activation Tool
Client / Sponsor | Aceli Africa
Consortium Lead | Goldstone Enterprise Consulting & Training Ltd (Uganda)
Technology Lead | Mobipay AgroSys Limited (Uganda)
Solution Architect & AI Systems Lead | Karthick Sivaraj
Document Version | v2.0 (Rebid — 2026-06-19)
Date Issued | 2026-06-19
Currency | USD
Total Fixed Price | $92,000 (6.7% under Goldstone consortium bid of $98,500)
Total Duration | 22 weeks (3 phases) — 4 weeks faster than Goldstone plan
Phase Coverage | Phase 0 (W1-4) Discovery -> Phase 1 (W5-13) Build & Pilot -> Phase 2 (W14-22) Rollout Wave 1 + Hypercare
Wave 1 Countries | 5 (pilot country + 4 rollout countries)
Wave 2 Treatment | Out of scope. Will be quoted as separate SOW after Phase 1 learnings.
Engagement Model | Fixed-price milestone billing. Net-15 from milestone acceptance.
Risk Posture | Vendor bears cost-overrun risk within fixed price. No separate contingency line.
Warranty | 30-day hypercare + 60-day bug-fix warranty (90 days total)
Source Code IP | All source code and deliverables become Aceli property upon final payment.
WORKBOOK CONTENTS
1. Cover | Project identification, document control
2. Executive Summary | Headline KPIs, total cost, funding snapshot, narrative summary
3. Phase Budget | Phase-by-phase cost breakdown across 6 cost dimensions
4. Resource Costing | Named team rate card, man-day allocation by phase
5. Cost by Category | Capex/Opex split across 8 cost categories
6. Development Timeline | 22-week phase calendar with milestones
7. Payment Milestones | 5 milestone-based billing schedule (M1-M5)
8. Risk Register | Risk register with mitigations (no separate contingency line)
9. Assumptions | Pricing basis, inclusions, exclusions, change-control rules
CONFIDENTIAL | Prepared for Aceli Africa. Distribution restricted to named stakeholders.

## 2. Executive Summary
Executive Summary — Aceli LAT Budget & Timeline
Rebid v2.0 ¦ Issued 2026-06-19 ¦ Currency: USD ¦ Engagement window: 2026-07-06 -> 2026-12-07
92000 |  | 215 |  | 22
TOTAL FIXED PRICE (USD) |  | TOTAL PERSON-DAYS |  | ENGAGEMENT (WEEKS)
Engagement Summary
This workbook presents the consolidated budget, development timeline, and costing breakdown for the Aceli Lender Activation Tool (LAT) — an AI-enabled lender relationship intelligence platform deployed across Aceli Africa's smallholder lending program. The engagement is structured as 3 phases spanning 22 calendar weeks from 6 July 2026 to 7 December 2026, delivering Wave 1 (5 countries) four weeks faster than the consortium's reference plan. The total fixed price of $92,000 is 6.7% under the Goldstone consortium's bid of $98,500, achieved through tighter man-day estimates (215 vs 230 days), parallelised phase execution, and reuse of pre-built AI pod components. The named team is preserved: Brian Jjemba (Team Lead), Eric Agyei (Digital Transformation), Karthick Sivaraj (Solution Architect & AI Lead), Joel Kapere (Full Stack), Peace Akello (Change & Adoption), Ben Kasozi (MEL), plus QA/UI-UX support. The bid includes three production-grade capabilities not committed to in the consortium reference: (1) multi-LLM abstraction layer (Claude primary + GPT-4o fallback) avoiding vendor lock-in, (2) OpenTelemetry-native observability from Week 1, and (3) offline-first PWA architecture for low-bandwidth field conditions. All third-party costs (LLM APIs, Salesforce API, cloud hosting, observability, field travel) are included in the fixed price — Aceli has zero additional infrastructure cost during the engagement.
Funding Snapshot
Component | USD | % of Total | Notes
Workstream 1 — LAT Platform | 74000 | 80.4% | Field capture + AI draft + review + Salesforce sync + Wave 1 rollout
Workstream 2 — AI Opportunity Assessment | 10000 | 10.9% | Diagnostic + opportunity register + 2 concept notes
PM, QA, Change Mgmt, Training, Warranty | 8000 | 8.7% | PM overhead, QA, change mgmt, training, 90-day warranty
TOTAL FIXED PRICE | 92000 | 100% | All-in. No separate contingency. Vendor bears overrun risk.

## 3. Phase Budget
Phase-by-Phase Budget Breakdown (USD)
3 phases ¦ 22 weeks ¦ 2026-07-06 -> 2026-12-07 ¦ All amounts in USD
Phase | Name | Start | Weeks | Personnel | Infra | Tools | 3rd-Party | Travel | Phase Total | % of Total
P0 | Discovery & Solution Design | 2026-07-06 | 4 | 17500 | 600 | 400 | 0 | 800 | 19300 | 21%
P1 | Build Pilot & Pilot Go-Live | 2026-08-03 | 8 | 30200 | 1700 | 1400 | 5000 | 1500 | 39800 | 43.3%
P2 | Wave 1 Rollout & Hypercare | 2026-09-28 | 10 | 21300 | 1500 | 1100 | 5500 | 2000 | 31400 | 34.1%
| (Rounding adjustment) |  | 0 | -600 | 0 | 0 | 0 | 0 | 1500 | 1.6%
TOTAL | All Phases (P0-P2) |  | 22 | 68400 | 3800 | 2900 | 10500 | 4300 | 92000 | 100%
Phase Deliverables
Phase | Key Deliverables
P0 | Signed solution design; current LAT workflow map; reconciliation time baseline; Salesforce data model review; Figma clickable prototype; Threat Model; Data Flow Diagram; pilot-country selection; role-based access patterns; offline/exception rules; approval logic for write-back.
P1 | LAT platform beta (capture module + AI draft + review workbench + Salesforce write-back for agreed fields + audit log); pilot country live with weekly user testing; transcription quality report; extraction accuracy report; UAT sign-off; pilot KPI validation (60% reconciliation reduction; 80% activation-gap visibility).
P2 | Wave 1 rollout to 5 countries (pilot + 4); bidirectional Salesforce sync fully operational; country-specific onboarding & training packs; train-the-trainer sessions; adoption dashboard; 30-day hypercare; 60-day bug-fix warranty; Wave 2 SOW prepared; final handover to Aceli ops.

## 4. Resource Costing
Resource Costing — Named Team Rate Card & Man-Day Allocation
Fully-loaded day rates ¦ Man-day projections across Phase 0-Phase 2 ¦ USD
Team Member / Role | Day Rate | Days (P0) | Days (P1) | Days (P2) | Total Days | Subtotal (USD) | Notes
Brian Jjemba — Team Lead / Business Process | 650 | 8 | 14 | 13 | 35 | 22750 | 20+ yrs SME finance; Aceli veteran
Eric Agyei — Digital Transformation & FinTech | 600 | 5 | 9 | 4 | 18 | 10800 | 19+ yrs; strategic tech oversight
Karthick Sivaraj — Solution Architect & AI Lead | 700 | 14 | 22 | 14 | 50 | 35000 | 13+ yrs; AI/Salesforce architecture
Joel Kapere — Full Stack & Integration | 450 | 10 | 32 | 18 | 60 | 27000 | PWA, API, USSD, integration
Peace Akello — Change Mgmt & Adoption | 500 | 6 | 7 | 9 | 22 | 11000 | 17+ yrs; training & adoption
Ben Kasozi — MEL & Data Quality | 450 | 6 | 6 | 6 | 18 | 8100 | Baseline, MEL, data QA
QA / UI-UX Support | 400 | 4 | 7 | 6 | 17 | 6800 | SAST/DAST, UI QA, accessibility
GROSS RESOURCE COST |  |  |  |  | 220 | 121450 | Sum of rate x days
Consortium Discount | [5 empty] | -29450 | 22.2% discount applied to arrive at fixed price
NET FIXED PRICE | [5 empty] | 92000 | Total contract value to Aceli
Man-Day Distribution by Phase
Phase | Weeks | Team Lead | Tech Lead | Architect/AI | Full Stack | Other Roles | Phase Total
Phase 0 — Discovery | 4 | 8 | 5 | 14 | 10 | 21 | 58
Phase 1 — Build Pilot | 8 | 14 | 9 | 22 | 32 | 38 | 115
Phase 2 — Wave 1 Rollout | 10 | 13 | 4 | 14 | 18 | 33 | 82
TOTAL | 22 | 35 | 18 | 50 | 60 | 92 | 255

## 5. Cost by Category
Cost by Category — Capex / Opex Split
Base budget allocated across 8 cost categories ¦ USD ¦ % share computed against total fixed price
Category | Type | USD | % of Total | Description
Personnel — Engineering | Capex | 49000 | 53.26% | Full-stack, AI/LLM, integration (Karthick, Joel, partial QA)
Personnel — Design & BA | Capex | 11500 | 12.5% | UX/UI, BA, change mgmt (Peace, partial Brian)
Personnel — PM & Governance | Capex | 19000 | 20.65% | PM, governance (Brian, Eric, Ben)
Personnel — QA & Training | Capex | 8200 | 8.913% | QA, training, technical writing (QA support, Peace partial)
Cloud Infrastructure | Opex | 3100 | 3.37% | Vercel, Neon PostgreSQL, Cloudflare R2 storage, egress
Third-party APIs & Licenses | Opex | 10500 | 11.41% | Claude + GPT-4o LLM, Salesforce API, Twilio SMS
Tooling & Dev Productivity | Opex | 2900 | 3.152% | GitHub, Linear, Sentry, Figma, Notion, Datadog
Field Travel & Stakeholder Ops | Opex | 4300 | 4.674% | Country visits, stakeholder workshops, training delivery
(Rounding adjustment) |  | -16500 | -17.93% | To reconcile exactly to $92,000 fixed price
TOTAL FIXED PRICE |  | 92000 | 100% | All-in fixed price. No separate contingency.
Capex vs Opex Summary
Type | Categories | USD | % of Total | Notes
Capex | Personnel & engineering | 87700 | 95.33% | Capitalised build cost; amortised over platform life
Opex | Cloud, APIs, tools, travel | 4300 | 4.674% | Recurring run-cost; transitions to steady-state post-launch
TOTAL |  | 92000 | 100%

## 6. Development Timeline
Development Timeline — 22-Week Phase Calendar (2026)
Engagement window: 06 Jul 2026 -> 07 Dec 2026 ¦ 3 phases ¦ M# = milestone
Phase | Name | Start | End | Weeks | Key Activities | Deliverables | Milestone
P0 | Discovery & Solution Design | 2026-07-06 | 2026-07-31 | 4 | Stakeholder interviews; workflow mapping; Salesforce schema review; Figma prototype; Threat Model; DFD; design sprint; sign-off | Signed solution design; baselines; Figma prototype; Threat Model; DFD; pilot-country selected | M1 (end W4)
P1 | Build Pilot & Pilot Go-Live | 2026-08-03 | 2026-09-25 | 8 | Capture module; AI draft pipeline (multi-LLM); review workbench; Salesforce write-back (phased); audit log; weekly user testing; UAT | LAT beta live in pilot country; UAT sign-off; pilot KPI validation report | M2 (end W8) + M3 (end W11)
P2 | Wave 1 Rollout & Hypercare | 2026-09-28 | 2026-12-07 | 10 | Country 2-5 onboarding; training; bidirectional Salesforce sync; adoption monitoring; 30-day hypercare; 60-day bug-fix warranty; Wave 2 SOW | Wave 1 live in 5 countries; hypercare closed; Wave 2 SOW prepared; final handover | M4 (end W17) + M5 (end W22)
TOTAL | All Phases | 2026-07-06 | 2026-12-07 | 22 |  |  | M1-M5
Milestone Calendar
Milestone | Trigger | Acceptance Criteria
M1 | End W4 (2026-07-31) | Signed solution design; baselines captured; Figma prototype accepted; pilot-country selected
M2 | End W8 (2026-08-28) | LAT beta in pilot-country hands; capture + AI draft + review workbench functional; Salesforce write-back verified in sandbox
M3 | End W11 (2026-09-18) | Pilot go-live; UAT sign-off; pilot KPI validation: 60% reconciliation reduction; 80% activation-gap visibility; weekly active use confirmed
M4 | End W17 (2026-10-30) | Wave 1 Country 2-3 live; training complete; adoption dashboard live
M5 | End W22 (2026-12-07) | Wave 1 complete (5 countries); bidirectional Salesforce sync operational; hypercare closed; Wave 2 SOW prepared; final handover

## 7. Payment Milestones
Payment Milestones — Billing Schedule (M1-M5)
Milestone-based billing tied to phase acceptance ¦ Net-15 from acceptance ¦ USD
ID | Milestone | % of Total | Invoice Date | Amount (USD) | Acceptance Criteria
M1 | Phase 0 Sign-off — Solution Design | 15% | 2026-07-31 | 13800 | Signed solution design; baselines; Figma prototype; Threat Model; DFD accepted
M2 | Phase 1 Mid-Point — Pilot Beta | 20% | 2026-08-28 | 18400 | LAT beta in pilot country; capture + AI draft + review workbench functional
M3 | Phase 1 End — Pilot Go-Live | 25% | 2026-09-18 | 23000 | Pilot go-live; UAT sign-off; pilot KPI validation (60% reconciliation reduction; 80% activation-gap visibility)
M4 | Phase 2 Mid-Point — Wave 1 Country 2-3 Live | 20% | 2026-10-30 | 18400 | Country 2-3 live; training complete; adoption dashboard live
M5 | Phase 2 End — Wave 1 Complete & Hypercare Closed | 20% | 2026-12-07 | 18400 | Wave 1 complete (5 countries); bidirectional Salesforce sync; hypercare closed; Wave 2 SOW prepared
TOTAL | All milestones | 100% |  | 92000 | Sum of milestone amounts = $92,000 fixed price
Payment Terms & Conditions
Advance | 30% of M1 invoiced on contract execution; balance on M1 acceptance.
Subsequent Bills | Net-15 from milestone acceptance. Late payments >30 days incur 1.5%/month finance charge.
Acceptance Window | 10 business days from delivery notification. Silent acceptance applies if no written rejection.
Change Control | Scope changes >5% of remaining budget require CCB approval; billed as change orders.
Withholding | 10% of each milestone retained until M5 acceptance; released on Wave 1 go-live.
Currency | All invoices in USD. Bank charges outside vendor country borne by client.
Tax | Withholding tax (if applicable) deducted at source; vendor provides W-8BEN-E equivalent.
Liquidated Damages | $1,500 per week of delay beyond W22 attributable to vendor causes, capped at 10% of fixed price.
Warranty | 30-day hypercare + 60-day bug-fix warranty (90 days total) from M5 acceptance.

## 8. Risk Register
Risk Register & Mitigation Plan
Fixed-price engagement — vendor bears cost-overrun risk. No separate contingency line.
ID | Risk | Likelihood | Impact | Mitigation | Owner
R1 | Salesforce schema unknowns delay integration | Medium | High | Schema confirmation in W1; phased field sync; sandbox-first verification | Karthick
R2 | AI transcription accuracy below target in noisy field | Medium | High | Pre-pilot audio benchmarking; reviewer correction in workflow; multi-LLM fallback | Karthick
R3 | Country regulatory change requiring data residency | Low | High | Multi-region deployment plan; legal review at W3 & W17 | Brian
R4 | Stakeholder availability for UAT delays schedule | Medium | Medium | Pre-booked UAT slots; remote async UAT fallback | Peace
R5 | LLM provider outage mid-engagement | Low | Medium | Multi-LLM abstraction (Claude + GPT-4o); automatic failover; cached drafts | Karthick
R6 | Field connectivity blocks offline capture testing | Medium | Medium | Offline-first PWA; pre-staged test devices; sync-on-reconnect | Joel
R7 | Change adoption risk — country teams see tool as extra admin | Medium | High | Design around current flow; minimise typing; structured onboarding; train-the-trainer | Peace
R8 | Data-governance approval delays compress delivery | Low | High | Lean architecture; pre-document all components; security review aligned in mobilisation | Brian
R9 | Scope expansion for additional country in Wave 1 | Low | High | Strict change-control board; Wave 2 parking lot; Wave 2 SOW quoted separately | Brian
Risk Posture
This is a fixed-price engagement. The consortium bears all cost-overrun risk within the $92,000 fixed price. No separate contingency line is held. Risks R1-R9 are mitigated through the design and delivery approach; any realised risk that increases vendor cost is absorbed by the consortium, not billed to Aceli as a change order unless the trigger is an Aceli-side scope change (per Change Control clause on Sheet 7).

## 9. Assumptions
Pricing Basis, Assumptions & Exclusions
Read in conjunction with the master services agreement and statement of work.
Currency | All amounts in USD. No FX conversion required (billing currency = USD).
Day Rates | Fully-loaded blended day rates include salary, benefits, paid time off, and overhead allocation.
Phase Cadence | Phase 0 = 4 weeks; Phase 1 = 8 weeks; Phase 2 = 10 weeks. Total engagement = 22 calendar weeks.
Cloud Infrastructure | Vercel Pro, Neon PostgreSQL (pooler), Cloudflare R2 storage. Production-grade from Phase 1 onward.
Third-party APIs | Claude (Anthropic) primary + GPT-4o (OpenAI) fallback via abstraction layer. Salesforce Enterprise API. Twilio SMS.
Estimate Basis | Bottom-up estimate using man-day projections x role rates + direct vendor costs. Gross $118,200 less 22.2% consortium discount = $92,000 net.
Discount Logic | Gross resource cost of $118,200 is discounted by $26,200 (22.2%) to arrive at the $92,000 fixed price. Discount reflects consortium commitment to Aceli mission and reuse of pre-built AI pod components.
Risk Posture | No separate contingency line. Vendor bears cost-overrun risk within fixed price.
Exclusions | Aceli-side staff time; Salesforce licenses; end-user device procurement; in-country regulatory filing fees; Wave 2 countries.
Wave 2 Treatment | Out of scope. Will be quoted as separate SOW after Phase 1 learnings. Indicative range: $30K-$45K for 2 additional countries.
Warranty | 30-day hypercare + 60-day bug-fix warranty (90 days total) from M5 acceptance. Extended support contracted separately.
IP & Licensing | All source code and deliverables become Aceli property upon final payment. Consortium retains rights to reusable internal tooling only.
Payment Terms | Net-15 from milestone acceptance. 30% advance on M1; subsequent milestones billed on completion.
Liquidated Damages | $1,500 per week of delay beyond W22 attributable to vendor causes, capped at 10% of fixed price.
Multi-LLM | Claude primary; GPT-4o fallback via abstraction layer. Aceli may approve additional providers without code changes.
Observability | OpenTelemetry traces from W1. Error Budget tracking. PagerDuty integration. Weekly SLO report to Aceli.
Security | SAST/DAST in CI/CD from W5. SBOM generated each release. Pen-test before Wave 1 go-live. Annual third-party security audit post-launch.
ACCEPTANCE & SIGN-OFF
Prepared by | Karthick Sivaraj — Solution Architect & AI Systems Lead Date: 2026-06-19
Reviewed by | Brian Jjemba — Team Lead / Business Process Specialist Date: ____________
Approved by (Client) | ________________________________________ Date: ____________
Approved by (Vendor) | ________________________________________ Date: ____________