## 1. Exec Summary
Aceli LAT — Goldstone vs Our Bid
Executive comparison summary ¦ All amounts in USD ¦ Issued 2026-06-19
Metric | Goldstone Consortium | Our Competitive Bid | Our Edge
Total Fixed Price (USD) | 98500 | 92000 | $6,500 cheaper (6.7% under)
Total Person-Days | 230 | 215 | 15 fewer days, same scope
Blended Day Rate (USD) | 428 | 428 | Same rate card parity
Engagement Window (weeks) | 26 | 22 | 4 weeks faster to Wave 1 live
Pilot Go-Live (week) | 13 | 11 | Pilot live 2 weeks earlier
Wave 1 Live (month) | 6 | 5 | Wave 1 complete 1 month earlier
Milestones | 3 phases | 5 milestones | Tighter billing governance
AI Provider Strategy | Claude only | Multi-LLM (Claude + GPT-4o) | No vendor lock-in
Observability | Not specified | OpenTelemetry from W1 | Production-grade SRE
Offline Capability | Implied | Offline-first PWA | Field-ready day 1
Source Code IP | Not specified | Full transfer on final payment | Aceli owns all code
Warranty Period | Within warranty line | 30-day hypercare + 60-day bug-fix | 3x longer support
Verdict
Our bid is $6,500 cheaper (6.7% under Goldstone), delivers Wave 1 four weeks faster, and includes three production-grade capabilities Goldstone's proposal does not commit to: (1) multi-LLM abstraction to avoid Anthropic lock-in, (2) OpenTelemetry-native observability from Week 1, and (3) offline-first PWA architecture for low-bandwidth field conditions. We retain the same named consortium team and the same Salesforce-as-system-of-record principle, so Aceli loses nothing on the trust/governance axis. Recommended action: submit our bid as the lead proposal with a short technical addendum covering the three differentiators above.

## 2. Technical
Technical Approach — Side-by-Side
Comparison of Goldstone's Technical Proposal vs Our Bid ¦ 2026-06-19
Dimension | Goldstone Consortium (Proposal) | Our Competitive Bid | Why Ours Is Better
Architecture Principle | Salesforce = system of record. LAT = field workflow + intelligence layer. Power BI = analytics. No shadow databases. | Same principle: Salesforce = system of record. LAT = field workflow + intelligence layer. We additionally commit to no-shadow-database guard in CI/CD. | Same principle; we add an automated guard.
Mobile / Field UX | Mobile-first design implied. Voice memo or typed note. Field capture on phone, tablet, laptop. | Offline-first PWA (installable). IndexedDB local queue. Sync-on-reconnect. Works in <100kbps networks. Same multi-device support. | Offline-first from day 1, not implied.
AI Drafting Pipeline | Managed speech-to-text. Claude for extraction + prompting. Human review before write-back. | Managed STT. Multi-LLM abstraction layer (Claude primary, GPT-4o fallback). Confidence-scored drafts with diff view. Human review before write-back. | Vendor resilience + transparent confidence.
Salesforce Integration | Standard Salesforce APIs. Approved write-back only. Phased field synchronisation. | Same approach: Salesforce REST/Bulk API, phased field sync, sandbox-first verification. Bidirectional sync by Month 5 (vs Month 6 in Goldstone plan). | Bidirectional sync 1 month earlier.
Governance & Audit | 4-stage governed workflow: capture -> AI suggestion -> human review -> approved write-back. Each stage generates auditable records. | Same 4-stage workflow. We add structured event log (append-only, hash-chained) + role-based review queue with SLA tracking. | Stronger audit trail + reviewer SLAs.
Exception Management | Routes low-confidence / incomplete / conflicting updates to manual review. | Same routing + reviewer-side explanation panel (showing why the AI flagged low confidence) + bulk-approve/reject for high-confidence batches. | Faster reviewer throughput.
Data Residency | Aceli-approved enterprise tenants. No vendor model training on Aceli data. | Same. We additionally publish a Data Flow Diagram in Week 3 and contractually commit to no-training in DPA. | Documented earlier + DPA-backed.
Observability / SRE | Not specified. | OpenTelemetry traces from Week 1. Error Budget tracking. PagerDuty integration. Weekly SLO report to Aceli. | Production-grade SRE baked in.
Security Review | Architecture kept lean. Pre-document components. Align security review in mobilisation. | Same + automated SAST/DAST in CI/CD from Week 5. SBOM generated each release. Pen-test before Wave 1 go-live. | Continuous security testing.
Training & Adoption | Role-based training. Country Managers, CDs, MEL, Product Design, Exec Office, sysadmins. | Same role matrix + 2 train-the-trainer sessions per country + in-app contextual help + adoption dashboard for Aceli HQ. | Sustainable adoption infrastructure.
Success Metrics | 60% reduction in reconciliation time. 80% structured activation-gap visibility. Monthly active use in pilot. | Same 3 metrics + 2 additional: AI draft acceptance rate >= 70% and reviewer time-per-update <= 90 seconds. | Tighter operational accountability.
Phase 0 Outputs | Current LAT workflow map. Reconciliation baseline. Salesforce data model review. Pilot selection criteria. Signed solution design. | Same outputs + interactive clickable Figma prototype (vs static design) + Data Flow Diagram + Threat Model. | Higher-fidelity Phase 0 deliverables.
Risks Identified | Salesforce config unknowns. Transcription variability. Change adoption. Governance approval delays. | Same 4 risks + 1 additional: LLM provider outage (mitigated by multi-LLM abstraction). | Broader risk coverage with mitigations.
Wave 2 Treatment | Not explicitly addressed. | Explicitly out of scope. Will be quoted as separate SOW after Phase 1 learnings. | Clearer scope boundary.

## 3. Commercial
Commercial Comparison — Side-by-Side
Goldstone's $98,500 bid vs Our $92,000 bid ¦ All amounts in USD
Line Item | Goldstone (USD) | Our Bid (USD) | Delta | Notes
Workstream 1 — LAT Platform | 78000 | 74000 | -4000 | We save $4K by reusing AI pod components
Workstream 2 — AI Opportunity Assessment | 12000 | 10000 | -2000 | Same scope; 1 less workshop
PM, QA, Change Mgmt, Training, Warranty | 8500 | 8000 | -500 | Same scope; tighter PM cadence
TOTAL FIXED PRICE | 98500 | 92000 | -6500 | 6.7% under Goldstone
Resource Costing (Gross)
Team Lead / Business Process (35 / 30 days @ $650) | 22750 | 19500 | -3250 | 5 fewer days; same rate
Digital Transformation & FinTech (20 / 18 days @ $600) | 12000 | 10800 | -1200 | 2 fewer days
Solution Architect & AI Systems (55 / 50 days @ $700) | 38500 | 35000 | -3500 | 5 fewer days; AI pod reuse
Full Stack Developer & Integration (60 / 60 days @ $450) | 27000 | 27000 | 0 | Same days; same rate
Change Mgmt & Adoption (25 / 22 days @ $500) | 12500 | 11000 | -1500 | 3 fewer days
MEL & Data Quality (20 / 18 days @ $450) | 9000 | 8100 | -900 | 2 fewer days
QA / UI-UX Support (15 / 17 days @ $400) | 6000 | 6800 | 800 | 2 more days for SAST/DAST
Gross Resource Cost | 127750 | 118200 | -9550 | Sum of above
Consortium Discount | -29250 | -26200 | 3000 | Net-back to fixed price
Net Resource Cost (= Fixed Price) | 98500 | 92000 | -6500 | Matches TOTAL FIXED PRICE
Third-Party / Cloud Costs (included in fixed price)
LLM API (Claude + GPT-4o) | Not specified | 4500 |  | Priced into our fixed bid
Salesforce API | Not specified | 1500 |  | Priced into our fixed bid
Cloud Hosting (Vercel + Neon + R2) | Not specified | 2200 |  | Priced into our fixed bid
Observability (OTel + Sentry) | Not specified | 1200 |  | Priced into our fixed bid
Field Travel & Workshops | Not specified | 2800 |  | Priced into our fixed bid
Total Third-Party / Cloud (included) | 0 | 12200 |  | Borne by us within fixed price

## 4. Timeline
Timeline Comparison — Side-by-Side
Goldstone's 26-week plan vs Our 22-week plan ¦ Weeks counted from contract kick-off
Weeks | Goldstone Plan | Our Plan | Phase | Milestone
W1-4 | Phase 0: Discovery, Salesforce schema review, design sprint, signed solution design | Phase 0: Same scope + Figma clickable prototype + Threat Model + Data Flow Diagram | Phase 0 | M1: Phase 0 Sign-off
W5-8 | Phase 1 begins: lender profile access, capture, transcription | Phase 1 (Build Pilot): Capture module + AI draft + review workbench (we compress from 9 to 8 weeks by parallelising) | Phase 1 | M2: Pilot Beta (end W8)
W9-13 | Phase 1 continues: structured extraction, reviewer approval, Salesforce write-back | Pilot live in pilot country with weekly user testing; bug-fixing + UAT in parallel | Phase 1 | M3: Pilot Go-Live (end W11)
W14-17 | (Goldstone still in pilot build) | Phase 2 (Rollout Wave 1): Country 2 + 3 onboarding, training, data migration | Phase 2 | M4: Wave 1 Country 2-3 Live (end W17)
W18-22 | (Goldstone still in pilot build / starting rollout) | Phase 2 continues: Country 4 + 5 onboarding, bidirectional Salesforce sync fully operational | Phase 2 | M5: Wave 1 Complete (end W22)
W23-26 | Phase 2: 5-country rollout, bidirectional Salesforce sync by M6 | Hypercare closed; handover to Aceli ops team; Wave 2 SOW prepared | Hypercare
Key Timeline Differences
1. Our pilot goes live at end of Week 11 vs Goldstone's end of Week 13 — 2 weeks earlier.
2. Our Wave 1 completes at end of Week 22 vs Goldstone's Month 6 (≈ Week 26) — 4 weeks earlier.
3. We achieve bidirectional Salesforce sync by Week 22 vs Goldstone's Month 6.
4. We compress Phase 1 from 9 weeks to 7 weeks by parallelising capture module and AI draft workstreams.
5. We use Week 23-24 for hypercare close-out (vs Goldstone who runs hypercare as part of rollout).

## 5. Recommendation
Recommendation — Submit Our Bid
Strategic rationale for submitting our $92,000 bid against Goldstone's $98,500 bid
Topic | Recommendation
Strategic Positioning | Position our bid as the lead proposal with three differentiators: (1) 6.7% lower price, (2) 4 weeks faster to Wave 1 live, (3) production-grade observability and multi-LLM abstraction that Goldstone does not commit to.
Pricing Posture | Hold firm at $92,000. Do not discount further. The 6.7% discount is sufficient to win on price; deeper discounting signals lack of confidence and erodes margin below sustainability.
Technical Addendum | Prepare a 4-page technical addendum covering: multi-LLM architecture, OpenTelemetry SLOs, offline-first PWA design, and the 3 additional Phase 0 deliverables (Figma prototype, Threat Model, Data Flow Diagram).
Risk Posture | Acknowledge we bear cost-overrun risk within the fixed price. Frame this as alignment with Aceli's interest: we are incentivised to deliver on time and within scope because we eat the overrun.
Negotiation Walk-Away | If Aceli pushes below $88,000, walk away. Below $88K we cannot sustain the named team at the proposed day rates without compromising quality or scope.
Timeline Commitment | Commit contractually to the 22-week timeline with a liquidated damages clause: $1,500 per week of delay beyond Week 22 attributable to vendor causes, capped at 10% of fixed price.
Warranty | Offer 30-day hypercare + 60-day bug-fix warranty (90 days total) vs Goldstone's unspecified 'warranty services'. This is a material differentiator.
Wave 2 Strategy | Explicitly exclude Wave 2 from this SOW. Quote Wave 2 separately after Phase 1 learnings (target: $30K-$45K for 2 additional countries). This protects our margin and gives Aceli optionality.
Next Step | Approve this comparison + rebid workbook, then submit the technical addendum and revised commercial proposal to Aceli by 2026-06-23.